| School Self Evaluation : Area of Focus: Effectiveness of leadership and management of the school by them |  |  |  |
| --- | --- | --- | --- |
| Parameters | Strength | Weakness | Evidence |
| Monitoring the progress of the SDP and ensuring that all decisions are data driven | Meeting of the SDP in charges as well as members is held once a month. |  | Minutes of the meeting |
| Leaders vision and mission and how these reflect in all the other areas | Activities at school – Involvement and guidance at every step of programmes |  | Sports Day and other events at school. |
| Create a culture of innovation/initiating innovations in staff and students | Opportunities to plan and implement various programmes of the school, CBSE. |  | Events exhibited under each leadership |
| Set a culture of high expectations for students and teachers for learning | Setting targets of achievement of scores by students. |  | Minutes of meeting Lesson observation and timely feedback |
| Develop 21st Century skills in students i.e. make them future ready ( critical thinking, inquiry based learning, discovery based learning, application of concepts, problem solving, collaborative and exploratory learning, experiential learning, coding, computational skills, digital literacy, communication skills, adapting to change, being ethical and humane, leadership skills, creative skills, well – being of all) | A class room that makes all learning implementation. Children use the concepts during their sports and extracurricular activities. |  | Art exhibition Talent show Cabinet opportunities MUN |
| Engaging in teachers professional development and examining how it has strengthened the teaching learning process through effective implementation in classroom teaching | Implementation of learnings in workshops in the classroom. Lesson observation and feedback, Training by HODs to the subject group. |  | Orientation programme Workshop for teachers |
| Improving the quality of teaching learning and assessment and sustaining the improvements | Analysis of the result/subject average and class average. |  | Lesson observations and feedback for improvement |
| Create a culture of trust, and transparency to encourage positivity in students and staff | Regular meetings to motivate and guide with the plan of the school. |  | Honesty shop |
| Build an inclusive school culture to ensure equal and fair opportunities are provided to all | Opportunities are provided to each one based on their abilities and competency. |  | Lolly sticks, random roll numbers, opportunities for every student to participate in events. |
| Build second level leader competency at all levels by guiding and supporting them to set goals and solve problems on their own | Discussion on one to one basis by the Principal/Vice principal to support and guide. |  | Guiding the leaders |
| Guiding teachers through constructive feedback and action plans for improving their teaching skills | Action plan is discussed for improvement. |  | Joint observation and feedback by the Principal. |
| Effectiveness of maintaining all documents | Each area of SDP maintains the documents mostly in soft copy. |  | Registers and soft copies |
| Growth Model Framework (For self - review schools only)– (the degree to which a positive relationship is seen between outcomes for students and quality of teaching learning and assessment ) |  |  |  |
| Root Cause of weaknesses: (Type here) |  |  |  |

| Effectiveness of leadership and management of the school by them (Tick where appropriate) | Needs Significant Improvement | Fair | Good | Outstanding |
| --- | --- | --- | --- | --- |
|  |  |  | Good |  |

| School Development Plan for Effectiveness of leadership and Management of the school by them Academic year 2022-2024 Set goals that are SMART: (Specific, Measurable, Achievable, Relevant, Time Bound) |  |  |
| --- | --- | --- |
| GOAL1: A more effective implementation, continuous analysis and evaluation of the actions under SDP to support in the achievement of the goals during 2022-24 |  |  |
| ACTION 1: Doing it: Orientation/Induction will be completed for new teachers along with reiteration of the same for existing teachers. Monitoring, assessing and analysing the action: |  |  |
| Persons Responsible along with designation | For implementing the action: Leadership team | For monitoring, measuring,analysing the action and drawing inferences: SDP Leadership and Management |
| Time and Frequency | For implementing the action: Once- Last week of May 2022/23 | For monitoring, measuring,analysing the action: Once - Last week of June 2022/23 |
| Remarks for Achievement of Action 1 On the basis of the analysis self-reflect on the following and provide answers: - What is the progress seen in measurable terms at the end of every month? (based on ‘monitoring, measuring, analysing the action and drawing inferences’) (The newly appointed teachers were guided by the leadership team and On-boarding in charge. They were welcomed and briefed on their roles and responsibilities. The joining formalities were carried out through LMS. Buddy teachers were assigned for new newly appointed teachers who were taken through the Betweenus portal, HR Mantra, Beanstalk CCE) Induction programme was conducted for both the existing and new teachers for a week from 18 May 2023 to 31 May 2023. This included staff meetings, workshops and demo lessons by the Vice Principal and HODs. The Principal sir welcomed the new joinees and explained about the organisation and its policies. They even initiated the PIS resources and their implementation. They are assigned buddy teachers to assist them with all possible learning and doubts. During the workshop new activities were conducted to make classroom teaching effective. Follow up meeting was taken by Principal to ensure the new teachers smooth functioning at school. They were also briefed on Zero tolerance policy and its importance. - Is the action showing the required improvement? If not, what is the reason? - (Yes. All teachers are accustomed to the institution and its policies.) (Yes. All teachers are accustomed to the institution and its policies.) - What must be redone /redefined to ensure that the required improvement is achieved? (NA) (NA) |  |  |
| ACTION 2: Doing it: Discuss the entire SDP 2022-24 with all the teachers and communicate clearly to all stakeholders to ensure that all understand their role and responsibilities in achieving the goals set for the year. Monitoring, assessing and analysing the action:. Persons Responsible along with designation; For implementing the action: SDP Leadership and Management; For monitoring, measuring, analysing the action and drawing inferences: SDP Leadership and Management. Time and Frequency; For implementing the action: Once- 2nd week of June 2022/23; For monitoring, measuring, analysing the action: Once a term. Remarks for Achievement of Action 2 On the basis of the analysis self-reflect on the following and provide answers: - What is the progress seen in measurable terms at the end of every month? (based on ‘monitoring, measuring, analysing the action and drawing inferences’) (A Meeting of the staff was called upon on 10 June to brief the members of the SDP regarding their role and responsibilities. Each SDP area in-charge gave a presentation on the area goals and actions drafted. The same was carried out with the PTA members. Children were briefed about the SDP 2022-24. They too, having the knowledge of SDP, realized their responsibilities.) (A Meeting of the staff was called upon on 16 July to brief the members of the SDP regarding their role and responsibilities. Teachers were assigned into each of the SDP area so that all are part of the development plan. Each SDP area in-charge gave a presentation on the area goals and actions drafted. Children were briefed about the SDP 2022-24 during the assembly. The same was carried out with the PTA members. They too, having the knowledge of SDP, realized their responsibilities. Rules and regulations of the school are given during PTA and informed to students.) - Is the action showing the required improvement? If not, what is the reason? (Yes) (Yes) - What must be redone /redefined to ensure that the required improvement is achieved? (NA) (NA). |
| Success in Achieving Goal 1: End of Term1: (How far or close is the school in achieving the goal. Focus to be on measurement) Self-reflect and provide answers to the following questions: - What is the extent of progress seen at the end of Term I? Is it as per the schools expectations? If not, what is the reason? (An effective analysis and implementation was carried out during the Monthly meeting. The Principal and Vice Principal guided the in-charges to address the loopholes in achievement of the respective goals. The Zero Tolerance and Welfare in charges were guided to circulate survey form as per their action plan.) - What must be done differently to ensure that the goal is achieved? (Each in charge along with their team can work aggressively to ensure effective implementation of the actions.) |  |  |
| Success in Achieving Goal 1: End of Term 2 : - What is the extent of progress seen at the end of Term II?Is it as per the schools expectations?If not what is the reason? The stakeholders became aware of the Zero Tolerance undertaken by the organisation through the survey form. - If a goal is achieved, what must be done to sustain it? Regular meetings and be focused on the goal and actions of each area. |  |  |

| School Development Plan for Effectiveness of leadership and Management of the school by them Academic year 2022-2024 Set goals that are SMART: (Specific, Measurable, Achievable, Relevant, Time Bound) |  |  |
| --- | --- | --- |
| GOAL 2: To ensure a more effective analysis of each SDP area and revise or implement the new targets if achieved. |  |  |
| ACTION 1: Doing it: Conduct a meeting of the SDP area in-charges once a month to discuss the progress as per the plan. Monitoring, assessing and analysing the action: |  |  |
| Persons Responsible along with designation | For implementing the action: SDP Leadership and Management | For monitoring, measuring, analysing the action and drawing inferences: SDP Leadership and Management |
| Time and Frequency | For implementing the action: First Thursday of each month | For monitoring, measuring, analysing the action: Once in two months |
| Remarks for Achievement of Action 1 On the basis of the analysis self-reflect on the following and provide answers: - What is the progress seen in measurable terms at the end of every month? (based on ‘monitoring, measuring, analysing the action and drawing inferences’) (Four meetings of the SDP in-charges were conducted.) (Two meetings of the SDP in-charges were conducted to discuss the updating of drafts, compiling of evidence. Two actions are added in Teaching learning assessment based on observation. Student outcome area is sustaining with the goals and actions as they are partially achieved.) - Is the action showing the required improvement? If not what is the reason? (Yes) (Yes) - What must be redone /redefined to ensure that the required improvement is achieved? (NA) (NA) |  |  |
| Success in Achieving Goal 2: End of Term1: (How far or close is the school in achieving the goal. Focus to be on measurement) Self-reflect and provide answers to the following questions: - What is the extent of progress seen at the end of Term I? Is it as per the schools expectations? If not, what is the reason? (Each SDP area has implemented the actions and achieved measurable progress.) - What must be done differently to ensure that the goal is achieved? (NA) |  |  |
| Success in Achieving Goal 2: End of Term 2 : - What is the extent of progress seen at the end of Term II?Is it as per the schools expectations?If not what is the reason? SDP meetings were conducted and in-charges of each area discussed the progress. They also worked and provided suggestions for the other areas. - If a goal is achieved, what must be done to sustain it? Regular meetings formally or informally will be more often to discuss and analyse. |  |  |